## Slide 1: Project Scope Management
Dr. Adebiyi
Dr. Okesola
Mrs. Mosaku

## Slide 2: Introduction Scope Management
The project scope correspond to the business needs. It links specific deliverables to the business benefits and fulfills stakeholders’ expectation.
Scope management consists of the processes required to ensure that the project includes all the work required, and only the work required to complete the project successfully.
Project scope management is primarily concerned with defining and controlling what is included in the project and what is excluded.

## Slide 3: Introduction Scope Management (2)
The process of scope management includes the following:
Specification of Scope
Defining and documenting stakeholders’ needs to meet project objectives
Developing a detailed description of the project and product/service
Subdividing project deliverables and work into smaller more manageable components
Management of Scope Changes
Monitoring the status of the project and product scope and managing changes to the scope

## Slide 4: Introduction Scope Management(3)
Verification of Scope
Formalizing acceptance of the completed project deliverables
The word “scope” can be qualified as follows to describe its level of detail and evolution:
Scope statement – describes the major objectives and states the project deliverables
Scope description – describes the needs, main theme, and key components of the project

## Slide 5: Introduction Scope Management(4)
Scope definition – breakdown of the project corresponding to the functional requirements
Scope specification – comprehensive design of the project to be delivered
Scope of work – detailed definition of work to be performed under a contract or subcontracted for the completion of the project. Also called statement of work

## Slide 6: Specification of scope
The project scope refers to the work to be accomplished to deliver a product, a service, a result with specified features and function.
The project scope defines the features and functions that characterize a product, a service.
Scope planning is the process of progressively elaborating and documenting the project work that produces the product of the project .

## Slide 7: Key Documents – project scope development
The following are key documents in project scope development:
Needs assessment
Functional requirements and
Solution design
Need Assessment – the needs assessment document is a record of the stakeholder needs that motivate the development of the project solution. It is essential that these needs be well understood and agreed upon before the initial phase begins.

## Slide 8: Key Documents – project scope development (2)
Generally, it is not possible to meet all the needs within the time and budget available for the project.
The following are several purposes for the needs assessment:
Get and document stakeholder agreement on the needs that the project is to meet to ensure that the development starts off in the right direction, to avoid later redirection.

## Slide 9: Key Documents – project scope development (3)
Clearly describe the needs that the project will meet, as the first step toward defining scope requirements.
Document the process and results of stakeholder consensus, relative to conflicting needs.
Demonstrate to the stakeholders that their individual views have been incorporated.

## Slide 10: Figure 1:Need Assessment Template
Section | Contents
1.0 Purpose of document | It is a description of the needs that the project will meet. This is a vehicle for stakeholder feedback
2.0 Overview | This gives a brief overview of the project, describes the stakeholders and expected role of each
3.0 Referenced Document | This section list supporting documentation used and other resources useful in understanding the performing organization
4.0 Needs collection | This section describes the needs collection process used. Records of interviews and their results are included
5.0 Needs description | It describes clearly and fully the needs expressed by the stakeholders
6.0 Needs validation | This section describes the process and results of validating the collected needs with the stakeholders
7.0 Gap analysis | This describes the needs and compares it to the current situation. Gaps are identified and ranked by criticality and importance
8.0 Needs comparison | This describes conflicting needs. Options are compared on cost, ease of implementation or other agreed –upon criteria
9.0 Prioritization of needs | This section defines the process and results of prioritizing the needs and the rational for the selection

## Slide 11: Key Documents – project scope development (4)
Functional requirements
The functional requirements document defines all the major system functions, and describes for each a set of requirements: what the function does, and under what conditions, e.g., environmental, reliability and availability.
Solution Design
The solution design document defines the architecture, components, modules, interfaces and data for a system to satisfy the specified functional requirements.

## Slide 12: Key Documents – project scope development (5)
The project requirements and design documents progressively elaborate on the needs assessment to produce:
The characteristics of the product/service
The project deliverables
The project assumptions
The project exclusions
The project constraints
The acceptance criteria

## Slide 13: Project Planning
The purpose of project planning is to define the detailed parameters of a project and ensure that all the pre-requisites for project execution and control are in place.
Project planning is the process of converting the project scope into work to be performed and to quantity that work so as to arrive at a schedule and a budget.
Project planning is a systematic and structured approach to create a viable and realistic project plan and build a commitment for subsequent project execution.

## Slide 14: The Key Planning Steps
The project manager must first of all finalize both the project scope statement and project objectives.
Three main steps are then engaged in an iterative process as more detail is reached. The project is structured to identify and describe the work to be performed – this is work breakdown structure (WBS). Each piece of performed work is quantified to established it duration and cost – this is the estimation. The work is then sequenced to established its logical flow – this is the precedence analysis.

## Slide 15: The Key Planning Steps Cont. Work Breakdown Structure
The first step in project planning is to define all the work activities that have to be performed to fulfill the project scope.
Many techniques can be used to draft the total set of activities, from a simple “to do list” to fully structured hierarchical diagram.

## Slide 16: The Key Planning Steps Cont. Estimation
The work to be performed as identified in the WBS is estimated to arrive at a duration and a cost for each item.
The project manager must accept and make clear to all team members that estimates are based upon incomplete, imperfect knowledge and assumptions.

## Slide 17: The Key Planning Steps Cont. Prudence Analysis
Following work estimation, and prior to proceeding to developing the schedule, the activities are to be sequenced to build the logical flow of the work to be performed to fulfill the project objectives